## Slide 1
CARES Implementation Phase
Rollout #4 Personal Tax Kickoff
August 14, 2024

## Slide 2: Agenda
Discussion Topics | Presenters
Welcome & Introductions | Rebecca Hartman
CARES Program Overview Rollout #4 Scope, Objectives and Timelines | David Montgomery
Rollout #4 Plans | CARES Project Team
Workflows/Interfaces | Marissa Smith
Iteration Plan | Lisa Harrison
Data Migration Plans | Timothy Greene
Department of Taxation – Expected Involvement | Roy Robinson
Validate Stakeholder Feedback from Discovery Phase Standing Meeting Schedule Proposal | Rebecca Hartman
Open Discussion | All
Wrap-up | Rebecca Hartman
AGO Collections modernization initiative

## Slide 3: Rollout #4 - Program Overview, Scope & Objectives

## Slide 4: High Level Program Timeline
A phased implementation strategy minimizes risk by incrementally building out core system functionality in a logical, sequential manner
Initial Rollout
Lay the Foundation – Core functionality that will benefit all aspects of the business, including common Workflows, Integrations, Letters, and Reports
Add the Business but Keep it Simple – Leverage the foundation + a small but meaningful layer of business class-specific functionality
  Day forward – Focus on new certifications before adding conversion of old data
  Internal Process Only – Focus on internal workflows before adding external partner workflows
AGO Collections modernization initiative

## Slide 5: CARES Implementation Approach
Our implementation plan is a buildup of the holistic system as we complete each rollout. The entirety of common workflows, interfaces, letters and reports are considered as we build the solution resulting in 80% of the system being complete at end of Rollout #4. Currently, as we initiate Personal Income Tax, we have completed roughly 73% of all common workflows, interfaces, letters and reports!
AGO Collections modernization initiative

## Slide 6: Rollout #4 Scope and Objectives
AGO Collections modernization initiative
Program Scope
Our CARES Program Strategy continues to focus on implementing the new Collections System incrementally. We will phase in all supported clients by business class while focusing on validating that Debt Manager can handle our new certifications, and legacy accounts.
Rollout #4 Objectives:
implement the Personal Income Tax business class into Debt Manager for all new and active accounts
migrate active legacy accounts from CUBS to Debt Manager
implement TOPS/OTOPS Offsets
implement our Electronic Bankruptcy Interface with the Defense Logistics Agency
implement Ohio Lottery Commission Real-time Interface
conform to FTI compliance policies and practices
Implementation Items:
7 Workflows, 48 to review
22 Interfaces
53 Letters
3 Reports
Notes: Read Slide

## Slide 7
AGO Collections modernization initiative
Rollout #4 – Timeline
Rollout #4 - Personal Income Tax |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Week Ending | 26-Jul-24 | 23-Aug-24 | 20-Sep-24 | 18-Oct-24 | 15-Nov-24 | 13-Dec-24 | 10-Jan-25 | 7-Feb-25 | 7-Mar-25 | 4-Apr-25 | 2-May-25 | 16-May | 30-May | 13-Jun-25 | 11-Jul-25 | 1-Aug-25 | 22-Aug-25 | 
Rollout #4 | Iteration | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 |  |  |  |  |  | Live
PTAX Implementation Workstream |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Project Initiation | Iteration 1 | Iteration 2 | Iteration 3 | Iteration 4 | Iteration 5 | Iteration 6 | Iteration 7 | Iteration 8 |  |  |  |  |  |  |  |  | 
 |  |  | C&R SIT 1 | C&R SIT 2 | C&R SIT 3 | C&R SIT 4 | C&R SIT 5 | C&R SIT 6 | C&R SIT 7 | C&R SIT 8 |  |  |  |  |  |  |  | 
 |  |  |  | AGO System Testing 1 | AGO System Testing 2 | AGO System Testing 3 | AGO System Testing 4 | AGO System Testing 5 | AGO System Testing 6 | AGO System Testing 7 | AGO System Testing 8 | AGO System Testing |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  | AGO Regression and E2E System Testing |  |  | AGO Performance Testing |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  | C&R Regression and E2E System Testing |  |  | C&R Performance Testing |  |  |  | Cutover Prep | Go Live
 |  |  |  |  |  |  |  |  |  |  |  |  | User Acceptance Testing |  |  |  | Dress Rehearsals | 

## Slide 8: Rollout #4 Key Milestones
AGO Collections modernization initiative
Rollout #4 Milestone | Start Date | End Date | Status
Project Initiation | 7/1/24 | 7/26/24 | Completed
Iteration #1 | 7/29/24 | 8/23/24 | In Process
Iteration #2 | 8/26/24 | 9/20/24 | 
Iteration #3 | 9/23/24 | 10/18/23 | 
Iteration #4 | 10/21/24 | 11/15/24 | 
Iteration #5 | 11/18/24 | 12/13/24 | 
Iteration #6 | 12/16/24 | 1/10/25 | 
Iteration #7 | 1/13/25 | 2/7/25 | 
Iteration #8 | 2/10/25 | 3/7/25 | 
End-to-End System Testing | 3/10/25 | 5/16/25 | 
User Acceptance Testing | 5/19/25 | 8/1/25 | 
Go Live | 8/4/25 | 8/25/25 | 

## Slide 9
Rollout #4 Plans

## Slide 10
Rollout #4 PTX Scope – Workflows
C&R Software to configure 7 workflows and assess the reuse of 48 workflows from prior rollouts for change as identified below. Assumption is they will not change.
AGO Collections modernization initiative
New Workflows
Innocent Spouse
Tax Collections
Tax Memos
Tax Penalty Abatements
Tax FTP Process
TOPS and OTOPS Offset
Creditor Setup - PTAX

## Slide 11
Rollout #4 PTX Scope – Interfaces
C&R Software to configure 22 interfaces as identified below.
AGO Collections modernization initiative
Interfaces
Transaction Export (IB.8050)
NonFin Export (IB. 8050.40)
Data Extract (8050.98)
Data Extract (8050.99)
Address Update (9008)
Transaction Import(9011)
Non-Financial (9011.40)
Cert (9020)
Decert (9407.40)
True Up Web Service (8405.40)
TOPS/OTOPS Send File
Interfaces
TOPS/OTOPS Collections File
TOPS/OTOPS Error File
TOPS/OTOPS Debt Balance Inbound
SOVOS – 1099
OIC Application Intake
OIC Compliance Check Request
OIC Compliance Check Response
Unclaimed Funds – Match Request Outbound
Unclaimed Funds – Match Request Inbound
Key Bank – XBKY, XOIC
TCI – Trustee Checks

## Slide 12: Rollout #4 – Iteration Plan
Iteration 1
Workflows
Skip Trace
Personal / SD Tax Collections
Creditor Setup
Integration
Certifications 9020
SOVOS-1099
Skip Trace – Request File
Skip Trace – Response File
Other
Letters Related to Tax Collections
Iteration 2
Workflows
Rework Workflows (Accounting, Legal and Forwarding) Integration
Address Update 9008
NonFinancial 9011.40
Decertification 9407.40
Transaction Import 9011
True-Up Web Service 8405.40
Other
Letters/Reports
Roles/Privileges
Iteration 3
Workflows
TOPS and OTOPS
Liens Letter Batching
Other
Letters/Reports
Iteration 4
Workflows
Offer in Compromise (OIC)
Integration
TOPS / OTOPS Send File
TOPS / OTOPS Collections File
TOPS / OTOPS Error File
TOPS / OTOPS Debt Balance Inbound
Other
Letters/Reports
Iteration 5
Workflows
Tax Memo
Integration
OIC – Compliance Check Request (OB)
OIC – Compliance Check Response (IB)
OIC Application Intake
Other
Letters/Reports
Scope is sequenced and prioritized in the Iteration Plan based on risk, business value, and their dependency on other functionality and priorities.
AGO Collections modernization initiative
The final timeline for Rollout #4 is “under discussion” and subject to change based upon finalizing plans in Iteration #1.

## Slide 13: Rollout #4 – Iteration Plan
Iteration 6
Workflows
Tax FTP Process
Tax Penalty Abatements
Integration
OIC Application Intake
Other
Letters / Reports
Iteration 7
Workflows
Tax Penalty Abatements
Integration
Unclaimed Funds – Match Request (OB)
Unclaimed Funds – Match Request (IB)
Transaction Export (IB.8050)
NonFinancial Export (IB.8050.40)
KeyBank – XBKY, XOIC
TCI – Trustee Checks
Other
Letters/Reports
Iteration 8
Workflows
Custom Card 1
Custom Card 2
Custom Card 3
Integration
TCI – Trustee Checks
Data Extract 8050.98
Data Extract 8050.99
Other
Letters/Reports
Continued.
AGO Collections modernization initiative
The final timeline for Rollout #4 is “under discussion” and subject to change based upon finalizing plans in Iteration #1.

## Slide 14
Rollout #4 PTX Scope – Data Migration
AGO Data Migration Team to migrate legacy Tax data and accounts to Debt Manager.
AGO Collections modernization initiative
Data Migration
Includes all PTAX new certifications and accounts
AGO Data Migration Team to extract active accounts from CUBS data and upload to Debt Manager
AGO Data Migration Team and Collections to parse, normalize, cleanse and transform legacy data
AGO Data Migration Team and C&R Software to reconcile conversion results

## Slide 15
Our data migration approach was created with the intent to ensure legacy CUBS data is extracted in a quality manner for uploading into Debt Manager. Our objective is for this to be seamless with limited impact on our clients. The new Debt Manager System enforces quality editing, formatting and standards upfront (unlike CUBS), so our approach is to apply these data rules when new certifications are submitted for loading into the new Debt Manager System for minimizing impact on our clients.
The following are for your awareness in our approach:
Conversion of data from CUBS to Debt Manager will take place in the days leading up our planned launch. During that time, there may be a freeze of sending CUBS files in the old layout while the CUBS data is being converted. We will communicate any anticipated freeze times in advance; however, you should be prepared to send any new certifications using the new CCI file layout.
We are currently identifying and applying data cleansing rules against existing CUBS data to ensure the migrated data meets the standards of the new system. We're also working with a cross-functional team to compare data between CUBS and Debt Manager to ensure all data is valid and mapped appropriately prior to the launch of Debt Manager.
AGO Collections modernization initiative
Rollout #4 – Data Migration Approach

## Slide 16
Taxation will be included in design phase. Though we are not expecting code changes based upon initial designs during Discovery and prior Rollouts, we will work with Taxation for any changes to layout. We will expect Taxation to provide/process test files and supporting any testing needed.
AGO Collections modernization initiative
Taxation’s Expected Involvement
Area | Involvement | Estimated Timeframes | Comments
Interface Inbound (From Tax) Certification File, Decertification file Address Update, NonFinancial file Transaction Import True Up Web Service | Design, Testing | Late Aug/Sept Testing May 2025 | Possible changes based upon design
Interface Outbound (to Tax) Transaction Export, Data Extract NonFinancial File Export OIC Compliance Check Request (both) | Design, Testing | Nov/Dec Testing May 2025 | Possible changes based on design
Client Inventory & Recon Outbound | Testing | Ready Now | Designs completed in R3 with all AGO clients including Taxation
Data Migration | Validation & Testing | Feb - Apr | 

## Slide 17: Validation of Stakeholder Feedback

## Slide 18: Validation of Stakeholder Feedback
Pain Points
Current collections system is inefficient and not programmed to handle certain aspects of the collections process, necessitating manual intervention (i.e., Tax memos process)
Concerns around Client Invoicing as it relates to the current Compass Reports system
Concerned about system access for Debt Manager (as some Tax Examiners can currently access debtors in CUBS directly)

## Slide 19: Validation of Stakeholder Feedback
Critical Success Factors for PTAX
Training is paramount
Accurate reporting is critical
Less manual review/intervention
Seamless integration between DM and OH Tax

## Slide 20: Validation of Stakeholder Feedback
PTAX IT Concerns
Ensuring the webservice integration for Debt Manager is implemented successfully
Maintaining open lines of communication between AGO ITS & Taxation IT

## Slide 21: Proposed Standing Meeting Cadence
Frequency: Bi-weekly
Day/time: Wednesdays at 11 am
Duration: 1 hour
First three meeting dates:
  August 14, 2024
  August 28, 2024
  September 11, 2024

## Slide 22: Bi-Weekly Meeting – Proposed Agenda
Current Status
Accomplishments
Obstacles/Issues/Risks
Schedule Review
  Next 30 Days
Action Items
Resources Check-in
Comments/Questions

## Slide 23
Thank You!