## Slide 1
CARES Implementation Phase
Rollout #4 PTAX Bi-Weekly
September 25, 2024

## Slide 2: Agenda
Schedule Review
Workflows Progress
ETL Design and Testing Timeline
Testing Considerations
Pain Points/Concerns Review
Resources Check-in / Design Session Feedback
Comments/Questions
AGO Collections modernization initiative

## Slide 3: Schedule Review
We are here

## Slide 4: Non-Technical Workflows
Design Session | AGO Owner | Dates Held | Comments
WF-19 Innocent Spouse | Kevin Whitacre, Nicole Brock | 8/5/2024-8/13/2024 | Deployed for AGO QA testing
WF-48 Tax Collections | Sharnee Jennings, Nick Yono | 7/29/2024-8/23/2024 | Formal approval stage
Skip Trace | Shannon Ray, Lucas Ward | 6/26/2024-8/12/2024 | Deployed for AGO QA testing
Workflow Look-backs | Sharnee Jennings, Nick Yono | 8/26/2024-present | Ongoing through iteration 2

## Slide 5: Technical Workflows
Design Session | AGO Owner | Dates Held | Comments
SOVOS-1099 | David Boals, James Seeto | 8/1/2024-8/20/2024 | Deployed for AGO QA testing
Skip Tracing Interface | Shannon Ray, Lucas Ward | 6/26/2024-8/21/2024 | Deployed for AGO QA testing
BKY Skip Tracing | Shannon Ray, Lucas Ward, Trish Lazich | 8/5/2024-8/12/2024 | Deployed for AGO QA testing
Migration Discussions | Billy Miller, Timothy Greene | 7/29/2024-Present | Ongoing Migration discussions; first look at mapping in progress
Certification (9020) Interface | Sharnee Jennings, Nick Yono | 8/26/2024-8/29/2024 | Formal approval stage
Address update 9008 | Sharnee Jennings, Nick Yono | 8/29/2024-9/5/2024 | Formal approval stage
Non-Financial 9011.40 | Sharnee Jennings, Nick Yono | 9/3/2024-9/5/2024 | Formal approval stage
Decert 9407.40 | Sharnee Jennings, Nick Yono | 9/5/2024 – Present | Formal approval stage
Transaction Import 9011 | Sharnee Jennings, Nick Yono | 9/9/2024 – Present | Final walk-through completed
True Up Webservice | Sharnee Jennings, Nick Yono | 9/17/2024 – Present | Discussions ongoing; paused

## Slide 6: Design and Testing for ETLS

## Slide 7: Testing Considerations
Test Topic/Item | Considerations/Scenarios Summary
9020 – New Cert Files | PIT and PSD accounts with varying criteria for addresses, filing statuses, abatements, BKY considerations, primary/secondary owners, and various cert reasons; recertify assessments that were previously decertified (native and converted)
9011 – Adjustments and Payments | Payments made to ODT, offset payments, return filed on DQ assessment, abatements, amended returns, forwarded accounts payment processing, reversals (including reversals in first test file and reversing transactions that were part of the first 9011 test file)
9011.40 – Non-Financial Adjustments | BKY adjustments of varying types, adding/closing receiverships, adding DOD (primary/secondary), update school district number
9008 – Address Updates | Primary/mailing addresses, name 1/name 2 updates, zip+4/5-digit zip updates, foreign addresses, phone number updates (home/cell), and long name and dba updates
8050 – Echo back from AGO for 9011 processing | Full payment including AG fees, full payment of Tax balance only, Partial payments (covering multiple buckets and single bucket only), PIF payment to PSD after making whole, applying PIF payment to PIT debt, and applying NSF charge
8050 – Echo from 9011 & AGO payment reversals | Reverse full payments, partial payments, PIF payments, and NSF charges mentioned above
8050.4 – AGO Non-Financial File | Add/discharge BKY, alter/add a lien, liquor permit recommendations, receivership updates, and account status
9407.4 – Decertify Assessments | Decertify native and converted assessments from collections or due to null and voids (various scenarios)
8050.98 and 8050.99 Active and Archive Files | Ensure all fields are transmitting properly as discussed during design sessions

## Slide 8: Validation of Stakeholder Feedback
Pain Points/Concerns - Updated
Current collections system is inefficient and not programmed to handle certain aspects of the collections process, necessitating manual intervention (i.e., Tax memos process, payment error reports, etc.). Ongoing internal and design session discussions taking place.
Concerns around Client Invoicing as it relates to the current Compass Reports system. Ongoing internal discussions taking place.
Concerned about system access for Debt Manager (as some Tax Examiners can currently access debtors in CUBS directly), and ensuring that their agents should only be able to view and add notes. Will be addressed systematically through roles set for each user.
Concerns re: eliminating debt by bucket. Ongoing internal discussions taking place.
Concerns about AGI/CC calculating and being removed appropriately, both manually and when Tax passes an adjustment to the AGO for updates. Reviewing in design.
AGO processing overpayments without Tax memo/prompting. Ongoing internal discussions taking place.
Out of statute overpayments following Tax Statute and allowing adjustments to pass to DM accordingly. Ongoing internal discussions taking place.
Ease of taxpayer registration for the payment portal (out of scope)
TOPS notices – can the AGO send? Ongoing internal discussions taking place.

## Slide 9: Resource Check-in / Design Session Feedback

## Slide 10: Comments/Questions

## Slide 11
Thank You!