## Slide 1
CARES Implementation Phase
Rollout #4 PTAX Monthly Touch Point
February 5, 2025

## Slide 2: Agenda
Schedule Review
Workflows Progress
ETL Design and Testing Timeline
Comments/Questions
AGO Collections modernization initiative

## Slide 3: Schedule Review
We are here

## Slide 4: Non-Technical Workflows
Design Session | AGO Owner | Dates Held | Comments
WF-19 Innocent Spouse | Kevin Whitacre, Nicole Brock | 8/5/2024-8/13/2024 | QA Testing completed; Awaiting End-to-End Testing
WF-48 Tax Collections | Sharnee Jennings, Nick Yono | 7/29/2024-8/23/2024 | AGO QA Testing in progress
Skip Trace | Shannon Ray, Lucas Ward | 6/26/2024-8/12/2024 | QA Testing completed; Awaiting End-to-End Testing
Workflow Look-backs | Sharnee Jennings, Nick Yono | 8/26/2024-9/27/2024 | Wave 1 deployed for AGO QA testing
AC-14 TOPS/OTOP | AGO Accounting/Pat Brobeck/Sharnee Jennings, Nick Yono | 9/30/2024-10/1/2024 | AGO QA Testing in progress
WF-33 Offer in Compromise | Kevin Whitacre/Nicole Brock | 10/21/2024-11/14/2024 | Formal Approval Stage
WF-55 Tax FTP Process | Sharnee Jennings, Nick Yono | 11/19/2024 | Formal Approval Stage
WF-50 Tax Penalty Abatements | Sharnee Jennings, Nick Yono | 12/5/2024-12/13/2024 | Formal Approval Stage

## Slide 5: Non-Technical Workflows
Design Session | AGO Owner | Dates Held | Comments
OIC Custom View | Nicole Brock; Kevin Whitacre | 12/5/2024-12/17/2024 | Final Walk-Through completed
WF-49 Tax Memos | Sharnee Jennings/Nick Yono | 1/7/2025 | In testing with C&R
Transaction Request Custom View | Sharnee Jennings, David Boals, Kevin Whitacre, Daniel Tharp, Jennifer Zap | 1/23/2025 - Present | Design sessions in progress

## Slide 6: Technical Workflows
Design Session | AGO Owner | Dates Held | Comments
SOVOS-1099 | David Boals, James Seeto | 8/1/2024-8/20/2024 | QA Testing completed; Awaiting End-to-End Testing
Skip Tracing Interface | Shannon Ray, Lucas Ward | 6/26/2024-8/21/2024 | AGO QA Testing in progress
BKY Skip Tracing | Shannon Ray, Lucas Ward, Trish Lazich | 8/5/2024-8/12/2024 | AGO QA Testing in progress
Migration Discussions | Billy Miller, Timothy Greene | 7/29/2024-Present | Ongoing Migration discussions taking place; fifth iterative load has been completed and results are currently under review.
Certification (9020) Interface | Sharnee Jennings, Nick Yono | 8/26/2024-8/29/2024 | AGO QA Testing in progress
Address update 9008 | Sharnee Jennings, Nick Yono | 8/29/2024-9/5/2024 | QA Testing completed; Awaiting End-to-End Testing
Non-Financial 9011.40 | Sharnee Jennings, Nick Yono | 9/3/2024-9/5/2024 | QA Testing completed; Awaiting End-to-End Testing
Decert 9407.40 | Sharnee Jennings, Nick Yono | 9/5/2024 – 9/23/2024 | AGO QA Testing in progress

## Slide 7: Technical Workflows - Continued
Design Session | AGO Owner | Dates Held | Comments
Transaction Import 9011 | Sharnee Jennings, Nick Yono | 9/9/2024 – 9/16/2024 | QA Testing completed; Awaiting End-to-End Testing
TOPS/OTOP Interface | Patrick Brobeck, Sharnee Jennings, Nick Yono | 9/30/2024-11/12/2024 | AGO QA Testing in progress
True Up Webservice | Sharnee Jennings, Nick Yono | 9/17/2024 – Present | Formal approval stage Current approach: Tax developer working with C&R developer support to adjust OHTax programming to call DM Rest API. Delivery/QA rough estimate – late January 2025.
Transaction Export IB.8050 | Sharnee Jennings, Nick Yono | 1/10/2025-2/4/2025 | Final Walk-Through completed
Non-Financial Export IB.8050.40 | Sharnee Jennings, Nick Yono | 1/10/2025-2/4/2025 | Final Walk-Through completed
DataExtract 8050.98/99 | Sharnee Jennings, Nick Yono | 1/17/2025-2/4/2025 | Final Walk-Through completed

## Slide 8: Design and Testing for ETLS

## Slide 9: Comments/Questions

## Slide 10
Thank You!